## 整理后
trice | description | project_code | project_name | organization_name | party_name | party_address | manager | corperation | legal_assignee | is_withholding_offsite | contract_code | contract_amount | change_amount | change_total_amount | settlement_amount | duty_paid_code | duty_paid_time | duty_paid_amount | capital_occupied | project_status | management_rate | management_plan_amount | management_real_amount | management_total_amount | management_owe_amount | party_billing_amount | party_billing_total_amount | collections_amount | collections_total_amount | collections_rate | customer_billing_amount | customer_billing_total_amount | payment_amount | payment_amount_clv | payment_amount_cliang | payment_amount_zdai | payment_total_amount | tax_rate | tax_plan_amount | tax_real_amount | tax_total_amount | tax_owe_amount | arrears_amount | expected_value | profile_point
2008-03-01 | 项目部表,第2行 | XMF08-02 | 中国国际贸易中心三期 | 项目部 | 中国国际贸易中心股份有限公司 | 北京市 | 柯秋惠 | 北京宇光装饰有限公司 | 柯秋惠 | 否 |  | 3950000 | 838394.62 |  | 4596964 |  |  |  |  | 完工 | 0.036 | 172382.2063 | 179181 | 179181 |  | 4986186.2 | 4986186.2 | 4986186.2 | 4986186.2 | 91.74% | 4931516.17 | 4931516.17 | 4979331.17 |  |  |  | 4979331.17 | 0.034 | 169530.3308 | 169529 | 169529 | 0
2010-04-15 | 项目部表,第3行 | XMF10-11 | 商品房A01楼等6项、商品房A04楼等5项 | 项目部 | 北京日月房地产开发有限公司 | 北京市 | 魏增坡 | 北京和平泛华装饰有限公司 | 魏增坡 | 否 |  | 4300000 | [7 empty] | 完工 | 0.036 | 154800 | 154800 | 154800 | 0 | 3940000 | 3940000 | 3940000 | 3940000 | 91.63% | 3814968.9 | 3814968.9 | 3908218.9 |  |  |  | 3908218.9 | 0.034 | 133960 | 133960 | 133960 | 0 |  | 65 | 亦庄
2010-11-09 | 项目部表,第4行 | XMF10-40 | 幸福三村 | 项目部 | 北京市第二建筑工程有限责任公司 | 北京市 | 江志真 | 北京美伦美门窗制品有限公司 | 江志真 | 否 |  | 842038 | [5 empty] | 253 |  | 完工 | 0.036 | 30313.368 | 30313 | 30313 | 0 | 700000 | 700000 | 700000 | 700000 | 83.13% | 693200 | 693200 | 693200 |  |  |  | 693200 | 0.034 | 23800 | 17000 | 17000 | 6800
2010-10-16 | 项目部表,第5行 | XMF10-51 | 中国传媒大学图书馆工程 | 项目部 | 北京市第三建筑工程有限公司 | 北京市 | 李春光 | 北京邦士富生物科技有限公司 | 李玉斌 | 否 |  | 1787170 | 868000 |  | 2610000 |  |  |  |  | 完工 | 0.036 | 93960 | 94830 | 94830 | 0 | 2610000 | 2610000 | 2410000 | 2410000 | 92.34% | 2356517 | 2356517 | 2407227.08 |  |  |  | 2407227.08 | 0.034 | 88740 | 88740 | 88740 | 0
2011-05-20 | 项目部表,第6行 | XMF11-21 | 永定华庭地下车库出入口外装饰幕墙 | 项目部 | [23 empty] | 0 | 0
2011-10-12 | 项目部表,第7行 | XMF11-48 | 生物技术研发中心二期 | 项目部 | 北京中关村生命科学院发展有限责任公司 | 北京市 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 否 |  | 21611588 | 2802330.83 |  |  | 0139123 | 2011-10-17 | 6484 |  | 完工 | 0.03 | 732417.5649 | 671920 | 671920 | 60497.5649 | 22758059.47 | 22758059.47 | 22758059.47 | 22758059.47 | 93.22% | 20358173.62 | 20358173.62 | 21886603.42 |  |  |  | 21886603.42 | 0.034 | 773774.022 | 773773 | 773773 | 0 |  | 140 | 管庄
2012-01-01 | 项目部表,第8行 | XMF12-01 | 北京邮件综合处理中心 | 项目部 | 中建二局第三建筑工程有限公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 1950000 | 6281535 |  |  | 9110694 | 2012-05-16 | 585 |  | 完工 | 0.03 | 246946.05 | 229500 | 229500 | 17446.05 | 8231535 | 8231535 | 8231535 | 8231535 | 100% | 7143200 | 7143200 | 8223072 |  |  |  | 8223072 | 0.034 | 279872.19 | 279872 | 279872 | 0 |  | 5 | 亦庄
2012-01-01 | 项目部表,第9行 | XMF12-02 | 门头沟新城冯村（一期）居住项目A西区 | 项目部 | 华润置地发展（北京）有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 3098310 |  |  |  | 0088619 | 2012-02-18 | 930 |  | 完工 | 0.036 | 111539.16 | 111539 | 111539 | 0 | 2463563 | 2463563 | 2463563 | 2463563 | 79.51% | 2225711.98 | 2225711.98 | 2424472.98 |  |  |  | 2424472.98 | 0.034 | 83761.142 | 83761 | 83761 | 0
2011-12-30 | 项目部表,第10行 | XMF12-03 | 空军9011工程空地勤综合楼 | 项目部 | 北京城建十六建筑工程有限责任公司 | 北京市 | 赵长亮 | 北京雄博兴业装饰设计有限公司 | 李国兵 | 否 |  | 3405024 |  |  |  | 0097964 | 2012-03-06 | 1175 |  | 完工 | 0.036 | 122580.864 | 122581 | 122581 | 0 | 3111296 | 3111296 | 3111296 | 3111296 | 91.37% | 2496087.77 | 2496087.77 | 3049860.32 |  |  |  | 3049860.32 | 0.034 | 105784.064 | 105784 | 105784 | 0 |  | 36 | 正和平
2012-01-01 | 项目部表,第11行 | XMF12-04 | 春晖园1#综合楼一段等4项工程 | 项目部 | 北京春晖园投资有限责任公司 | 北京市 | 纪树军 | 北京中建润泽建筑工程有限公司 | 李邦海 | 否 |  | 9708632.26 | 2846340 |  |  | 0097921 | 2012-03-07 | 2913 |  | 完工 | 0.03 | 376649.1678 | 362780 | 362780 | 13869.1678 | 12554972.26 | 12554972.26 | 11825835.49 | 11825835.49 | 94.19% | 10650362.28 | 10650362.28 | 11370776.64 |  | 17830 | 275 | 11388881.64 | 0.034 | 426869.0568 | 426869 | 426869 | 0 |  | 80 | 亦庄
2012-02-01 | 项目部表,第12行 | XMF12-05 | 北京绿地密云国际花都项目 | 项目部 | 北京绿地京宏置业有限公司 | 北京市 | 李金光 | 北京丰益宏业装饰有限公司 | 李金光 | 否 |  | 14568703.88 | 651269 |  |  | 0091571 | 2012-06-01 | 4371 |  | 完工 | 0.03 | 456599.1864 | 437061 | 437061 | 19538.1864 | 11975108 | 11975108 | 11054072 | 11054072 | 72.63% | 10047825.75 | 10047825.75 | 10954969.75 |  | 4010 |  | 10958979.75 | 0.034 | 407153.672 | 407154 | 407154 | 0 |  | 220 | 管庄、昌平
2012-02-01 | 项目部表,第13行 | XMF12-07 | 中国原子能科学研究院3号楼 | 项目部 | 北京城乡建设集团有限责任公司 | 北京市 | 曲刚 | 北京京业正通建筑材料有限责任公司 | 王艳 | 否 |  | 20000000 | 5102771 |  | 25102771 | 0097929 | 2012-03-13 | 6000 |  | 完工 | 0.03 | 753083.13 | 753083 | 753083 | 0 | 23847632.45 | 23847632.45 | 23847632.45 | 23847632.45 | 95% | 23095725.17 | 23095725.17 | 23847632.17 |  |  |  | 23847632.17 | 0.034 | 810819.5033 | 810820 | 810820 | 0 |  | 50 | 管庄
2012-02-01 | 项目部表,第14行 | XMF12-08 | 六郎庄拆迁安置房一标段 | 项目部 | 中国新兴建设开发总公司 | 北京市 | 付仁福 | 北京富恒兴达装饰工程有限公司 | 付仁福 | 否 |  | 33000000 |  |  |  | 5032993 | 2012-07-05 | 10752 |  | 完工 | 0.035 | 1155000 | 1155000 | 1155000 | 0 | 22720000 | 22720000 | 21720000 | 21720000 | 65.82% | 19634904.47 | 19634904.47 | 21702791.47 |  |  |  | 21702791.47 | 0.034 | 772480 | 772480 | 772480 | 0
2012-02-01 | 项目部表,第15行 | XMF12-09 | 六郎庄拆迁安置房二标段 | 项目部 | 中国中铁航空港建设集团有限公司北京第八分公司 | 北京市 | 付仁福 | 北京富恒兴达装饰工程有限公司 | 付仁福 | 否 |  | 20000000 |  |  |  | 5032982 | 2012-06-21 | 6465 |  | 完工 | 0.035 | 700000 | 700000 | 700000 | 0 | 18500000 | 18500000 | 17500000 | 17500000 | 87.5% | 16533332.5 | 16533332.5 | 17304686.41 |  |  | 2200 | 17306886.41 | 0.034 | 629000 | 629000 | 629000 | 0
2012-03-01 | 项目部表,第16行 | XMF12-11 | 京西宾馆东楼群房改建工程 | 项目部 | 上海建工七建集团有限公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 15000000 | 60000 |  |  | 0098166 | 2012-03-21 | 4500 |  | 完工 | 0.03 | 451800 | 450000 | 450000 | 1800 | 12400000 | 12400000 | 12400000 | 12400000 | 82.34% | 12114323.56 | 12114323.56 | 12399923.56 |  |  |  | 12399923.56 | 0.034 | 421600 | 421600 | 421600 | 0 |  | 25 | 亦庄
2012-04-01 | 项目部表,第17行 | XMF12-12 | 爱博精电生产楼等2项工程 | 项目部 |  | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 1315898 | [7 empty] | 完工 | 0.036 | 47372.328 |  |  | 47372.328 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0 |  | 6 | 三河
2012-03-20 | 项目部表,第18行 | XMF12-13 | 环能院实验楼幕墙工程 | 项目部 | 中国建筑技术集团有限公司 | 北京市 | 刘乃适 | 北京中适广发智能门有限公司 | 刘乃适 | 否 |  | 1523208.31 |  |  |  | 0099400 | 2014-04-19 | 538 |  | 完工 | 0.036 | 54835.4992 | 54835.5 | 54835.5 | 0 | 1294727.06 | 1294727.06 | 1294727.06 | 1294727.06 | 85% | 1049652.07 | 1049652.07 | 1294623.48 |  |  |  | 1294623.48 | 0.034 | 44020.72 | 44021 | 44021 | 0 |  | 20 | 管庄
2012-03-20 | 项目部表,第19行 | XMF12-14 | 印刷大楼改造工程 | 项目部 | 中国印刷总公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 3701841.55 | 4570557.65 |  |  | 0091567 | 2012-04-27 | 1049 |  | 正常进行 | 0.03 | 248171.976 | 248172 | 248172 | 0 | 7316811.73 | 7316811.73 | 7294401.45 | 7294401.45 | 88.18% | 6832563.96 | 6832563.96 | 7155469.46 |  |  |  | 7155469.46 | 0.034 | 248771.5988 | 248773 | 248773 | 0 |  | 57 | 三河
2012-03-21 | 项目部表,第20行 | XMF12-15 | 大兴黄村地铁枣园路站居住项目 | 项目部 | 北京城建建设工程有限公司 | 北京市 | 季长友 | 北京诚和信装饰装潢有限责任公司 | 鲍云锋 | 否 |  | 5578834.3 |  |  |  | 0099381 | 2012-03-24 | 1674 |  | 完工 | 0.036 | 200838.0348 | 200838 | 200838 | 0 | 3416000 | 3416000 | 3416000 | 3416000 | 61.23% | 3252562.45 | 3252562.45 | 3409775.64 |  |  |  | 3409775.64 | 0.034 | 116144 | 116144 | 116144 | 0 |  | 64 | 大兴
2012-03-30 | 项目部表,第21行 | XMF12-16 | 宇泰佳苑住宅楼 | 项目部 | 河南益通置业有限公司 | 河南郑州 | 熊斌 | 郭大龙 |  | 异地交税 |  | 5045600 | 118800 |  |  | 0099396 | 2012-04-13 | 1514 |  | 完工 | 0.036 | 185918.4 | 185919.85 | 185919.85 | 0 | 4624200 | 4624200 | 4737414.86 | 4737414.86 | 91.73% | 4276212.79 | 4276212.79 | 4737414.86 |  |  |  | 4737414.86 |  | 0 |  |  | 0 |  | 54 | 郭大龙
2012-04-07 | 项目部表,第22行 | XMF12-17 | 大兴黄村新城北区16号项目 | 项目部 | 北京金地融侨房地产开发有限公司 | 北京市 | 杨广 | 北京龙辰塑钢门窗公司 | 杨晓峰 | 否 |  | 4328546 |  |  |  | 5032998 | 2012-07-10 | 1299 |  | 完工 | 0.046 | 199113.116 | 199113 | 199113 | 0 | 3462837 | 3462837 | 3462837 | 3462837 | 80% | 3278949.26 | 3278949.26 | 3462635.86 |  |  |  | 3462635.86 | 0.034 | 117736.458 | 117737 | 117737 | 0 |  | 55 | 管庄
2012-04-01 | 项目部表,第23行 | XMF12-18 | 密云县穆家岭镇华润希望小镇展示 | 项目部 | 北京华润希望发展有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 416950 | 36973.6 |  | 453923.6 | 9110683 | 2012-05-03 | 126 |  | 完工 | 0.036 | 16341.2496 | 15010 | 15010 | 1331.2496 | 431228 | 431228 | 431228 | 431228 | 95% | 255500 | 255500 | 427020 |  |  |  | 427020 | 0.034 | 14661.752 | 14662 | 14662 | 0
2012-05-02 | 项目部表,第24行 | XMF12-19 | 京昌高科技信息产业园2#厂房 | 项目部 | 北京市昌平一建建筑有限责任公司第二分公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 1785000 |  |  |  | 9110684 | 2012-05-03 | 536 |  | 完工 | 0.036 | 64260 | 64260 | 64260 | 0 | 500000 | 500000 | 500000 | 500000 | 28.01% | 395996 | 395996 | 499041.97 |  |  |  | 499041.97 | 0.034 | 17000 | 17000 | 17000 | 0 |  | 20 | 管庄
2012-05-10 | 项目部表,第25行 | XMF12-20 | 总参气象水文局经济适用住房工程 | 项目部 | 北京城建七建设工程有限公司 | 北京市 | 吴荣 | 北京佳盛杰瑞商贸有限公司 | 季福成 | 否 |  | 2220000 | 351000 |  | 2571000 | 0091576 | 2012-06-15 | 666 |  | 完工 | 0.036 | 92556 | 92556 | 92556 | 0 | 1550000 | 1550000 | 1530000 | 1530000 | 59.51% | 954836 | 954836 | 1530000 |  |  |  | 1530000 | 0.034 | 52700 | 52700 | 52700 | 0 |  | 26 | 管庄
2012-05-01 | 项目部表,第26行 | XMF12-21 | 天津红星国际广场2#地酒店式公寓 | 项目部 | 天津市华运商贸物业有限公司 | 天津市 | 闫禄章 | 北京奥维尔建筑材料销售有限公司 | 闫禄章 | 异地交税 |  | 5473241 | 47753 |  | 5520994 |  |  |  |  | 完工 | 0.03 | 165629.82 | 164197 | 164197 | 1432.82 | 5520994 | 5520994 | 5244944.3 | 5244944.3 | 95% | 4583453.19 | 4583453.19 | 5238901.47 |  |  |  | 5238901.47 | 0.0374 | 206485.1756 |  |  | 0
2012-05-21 | 项目部表,第27行 | XMF12-22 | 老城厢12号地块 | 项目部 | 中建一局集团建设发展有限公司/天津中新名仕房地产开发有限公司 | 天津市 | 丁有智 | 沈阳市渤海保温门窗工程有限公司 | 丁有智 | 异地交税 |  | 36296483 | 1293588 | [6 empty] | 完工 | 0.03 | 1127702.13 | 1127608 | 1127608 | 94.13 | 33307394 | 33307394 | 33307394 | 33307394 | 88.61% | 28631226.4 | 28631226.4 | 33434705.17 |  |  |  | 33434705.17 | 0.0374 | 1245696.5356 |  |  | 0 |  | 320 | 管庄
2012-05-01 | 项目部表,第28行 | XMF12-23 | 现代农业生物研发平台工程 | 项目部 | 中铁建设集团有限公司 | 北京市 | 杨如林 | 北京和平芙蓉商贸有限公司 | 董宴春 | 否 |  | 3831227.57 |  |  |  | 5032991 | 2012-07-04 | 1150 |  | 完工 | 0.036 | 137924.1925 | 137924 | 137924 | 0 | 3831180 | 3831180 | 3030000 | 3030000 | 79.09% | 2725866.33 | 2725866.33 | 3007274.13 |  |  |  | 3007274.13 | 0.034 | 130260.12 | 130260 | 130260 | 0 |  | 31 | 亦庄
2012-06-13 | 项目部表,第29行 | XMF12-24 | 厂房一等4项铝合金门窗工程 | 项目部 | 格兰达投资管理（北京）有限公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 1444588.7 | 1770220.47 |  |  | 5033000 | 2012-07-11 | 966 |  | 完工 | 0.036 | 115733.1301 | 115733 | 115733 | 0 | 2500366.44 | 2500366.44 | 2500366.44 | 2500366.44 | 77.78% | 2230332.1 | 2230332.1 | 2492151.1 |  |  |  | 2492151.1 | 0.034 | 85012.459 | 85014 | 85014 | 0 |  | 31 | 三河
2012-07-02 | 项目部表,第30行 | XMF12-26 | 爱迪学校报告厅 | 项目部 | 北京爱迪学校 | 北京市 | 李春光 | 北京邦士富生物科技有限公司 | 李玉斌 | 否 |  | 1508400 |  |  |  | 5032989 | 2012-07-02 | 453 |  | 完工 | 0.036 | 54302.4 | 54302 | 54302 | 0 | 1190000 | 1190000 | 1199905 | 1199905 | 79.55% | 1152231.93 | 1152231.93 | 1192691.93 |  |  |  | 1192691.93 | 0.034 | 40460 | 40460 | 40460 | 0 |  | 7 | 管庄
2012-07-01 | 项目部表,第31行 | XMF12-27 | 中国劳动关系学院教学楼修缮工程 | 项目部 | 中国劳动关系学院 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 742782.79 | 149141.78 |  |  | 0099942 | 2012-07-19 | 223 |  | 完工 | 0.036 | 32109.2845 | 26920 | 26920 | 5189.2845 | 891924.57 | 891924.57 | 891924.57 | 891924.57 | 100% | 426993.57 | 426993.57 | 886924.57 |  |  |  | 886924.57 | 0.034 | 30325.4354 | 30405 | 30405 | -79.5646 |  | 8 | 三河
2012-07-27 | 项目部表,第32行 | XMF12-28 | 密云县穆家岭镇华润希望小镇乡村酒店 | 项目部 | 北京华润希望发展有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 328000 | 34031 |  |  | 0099956 | 2012-07-27 | 99 |  | 完工 | 0.036 | 13033.116 | 13033 | 13033 | 0 | 343930 | 343930 | 343930 | 343930 | 95% | 114435.82 | 114435.82 | 339814 |  |  |  | 339814 | 0.034 | 11693.62 | 11693 | 11693 | 0 |  | 4 | 管庄
2012-07-01 | 项目部表,第33行 | XMF12-29 | 春晖园1#综合楼一段等4项工程 | 项目部 | 北京春晖园投资有限责任公司 | 北京市 | 纪树军 | 北京中建润泽建筑工程有限公司 | 李邦海 | 否 |  | 4400000 |  |  |  | 0097769 | 2012-08-16 | 1320 |  | 完工 | 0.03 | 132000 | 132000 | 132000 | 0 | 4100000 | 4100000 | 3300000 | 3300000 | 75% | 3180103.71 | 3180103.71 | 3292303.71 |  |  |  | 3292303.71 | 0.034 | 139400 | 112200 | 112200 | 27200
2012-07-01 | 项目部表,第34行 | XMF12-30 | 天津国际城诗景颂苑二标段12#-16# | 项目部 | 中铁十三局集团有限公司 | 天津市 | 于洋 | 北京城建长城伟达装饰公司 | 孙国强 | 异地交税 |  | 5538662 | 3392971 | [6 empty] | 完工 | 0.03 | 267948.99 | 267949 | 267949 | 0 | 7570000 | 7570000 | 7570000 | 7570000 | 84.75% | 7355941.42 | 7355941.42 | 7552961.89 |  |  |  | 7552961.89 | 0.0374 | 283118 | 283118 | 283118 | 0
2012-07-18 | 项目部表,第35行 | XMF12-31 | 2011工程 | 项目部 | 中建一局集团第二建筑有限公司 | 北京市 | 霍林宝 | 中国人民解放军61159部队后勤部 | 霍林宝 | 否 |  | 8443771 | 1126543.36 |  |  | 0097761 | 2012-08-06 | 2534 |  | 完工 | 0.03 | 287109.4308 | 287109 | 287109 | 0 | 8599000 | 8599000 | 8599000 | 8599000 | 89.85% | 5958030.26 | 5958030.26 | 8594025.53 |  |  |  | 8594025.53 | 0.034 | 292366 | 292366 | 292366 | 0 |  | 72 | 亦庄
2012-07-23 | 项目部表,第36行 | XMF12-32 | 宝鼎商场 | 项目部 | 华美财务（北京）科技有限公司 | 北京市 | 王晨 | 北京润勤洲际建材有限责任公司 | 杨晓彬 | 否 |  | 4520000 |  |  |  | 0099952 | 2012-07-24 | 1356 |  | 完工 | 0.036 | 162720 | 162720 | 162720 | 0 | 4395540.75 | 4395540.75 | 3616000 | 3616000 | 80% | 3533736 | 3533736 | 3616000 |  |  |  | 3616000 | 0.034 | 149448.3855 | 149448 | 149448 | 0
2012-07-23 | 项目部表,第37行 | XMF12-33 | 朝阳区东坝驹子房农民安置房 | 项目部 | 北京市朝阳城市建设综合开发公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 8171765 |  |  |  | 0097768 | 2012-08-14 | 2452 |  | 完工 | 0.03 | 245152.95 | 245153 | 245153 | 0 | 6000000 | 6000000 | 6000000 | 6000000 | 73.42% | 5613614.35 | 5613614.35 | 5991760.6 |  |  |  | 5991760.6 | 0.034 | 204000 | 204000 | 204000 | 0 |  | 100 | 管庄
2012-08-07 | 项目部表,第38行 | XMF12-34 | 小屯新村B03、B06回迁楼及B04配套 | 项目部 | 北京绿林双泉房地产开发有限公司天鸿美域项目分公司 | 北京市 | 江志真 | 北京美伦美门窗制品有限公司 | 江志真 | 否 |  | 5170956.94 |  |  |  | 0097779 | 2012-08-29 | 1552 |  | 完工 | 0.03 | 155128.7082 | 155129 | 155129 | 0 | 4912409.09 | 4912409.09 | 4912409.09 | 4912409.09 | 95% | 4676282.45 | 4676282.45 | 4902104.45 |  |  |  | 4902104.45 | 0.034 | 167021.9091 | 167022 | 167022 | 0 |  | 16 | 亦庄
2012-08-09 | 项目部表,第39行 | XMF12-35 | 衙门口居住及公建项目 | 项目部 | 北京天石基业房地产开发有限公司 | 北京市 | 李智勇 | 北京通联门窗有限公司 | 吕松岩 | 否 |  | 7737463.35 |  |  |  | 3166153 | 2012-09-19 | 2321 |  | 完工 | 0.03 | 232123.9005 | 232124 | 232124 | 0 | 7737463.36 | 7737463.36 | 7737463.36 | 7737463.36 | 100% | 6908727.11 | 6908727.11 | 7736045.21 | 38 | 402 | 743 | 7737228.21 | 0.034 | 263073.7542 | 263074 | 263074 | 0 |  | 10 | 管庄
2012-08-09 | 项目部表,第40行 | XMF12-36 | 西北旺六里屯农民定置点定向房 | 项目部 | 中建一局集团第三建筑有限公司/中航天建设工程有限公司/北京昊海建设有限公司 | 北京市 | 王军 | 北京军建凯达幕墙装饰有限公司 | 秦存国 | 否 |  | 1615034.9 | 20970833.4 |  |  | 0097765 | 2012-08-13 | 485 |  | 完工 | 0.03 | 677576.049 | 677576 | 677576 | 0 | 19750000 | 19750000 | 18850000 | 18850000 | 83.46% | 16568345.4 | 16568345.4 | 18818897.61 |  |  |  | 18818897.61 | 0.034 | 671500 | 671500 | 671500 | 0
2012-09-03 | 项目部表,第41行 | XMF12-46 | 空军装备研究院防控所 | 项目部 | 北京朝林建设集团有限公司第四分公司 | 北京市 | 钱金花 | 北京笠融建筑工程有限公司 | 钱金花 | 否 |  | 20572132.07 |  |  |  | 3088688 | 2012-10-17 | 6981 |  | 完工 | 0.03 | 617163.9621 | 617164 | 617164 | 0 | 8450000 | 8450000 | 11402300 | 11402300 | 55.43% | 9476128.45 | 9476128.45 | 10916099.67 |  |  |  | 10916099.67 | 0.034 | 287300 | 287300 | 287300 | 0 |  | 55 | 管庄
2012-09-03 | 项目部表,第42行 | XMF12-47 | D型公寓D4一单元铝合金窗 | 项目部 | 北京春晖园文化娱乐有限责任公司 | 北京市 | 纪树军 | 北京中建润泽建筑工程有限公司 | 李邦海 | 否 |  | 500000 | 1680151.09 |  |  | 3166142 | 2012-09-03 | 220 |  | 完工 | 0.03 | 65404.5327 | 65405 | 65405 | 0 | 1736110.48 | 1736110.48 | 1681703.26 | 1681703.26 | 77.14% | 1289913.16 | 1289913.16 | 1348940.16 |  |  |  | 1348940.16 | 0.034 | 59027.7563 | 59027 | 59027 | 0 |  | 63 | 管庄
2012-09-20 | 项目部表,第43行 | XMF12-51 | 总政318信息化业务楼 | 项目部 | 中国人民解放军总政治部机关营建办公室 | 北京市 | 李玉朝 | 北京若愚装饰有限公司 | 杨书芳 | 否 |  | 7729248 | 364302 |  |  | 3088687 | 2012-10-17 | 2319 |  | 完工 | 0.03 | 242806.5 | 242806 | 242806 | 0 | 5370000 | 5370000 | 5370000 | 5370000 | 66.35% | 4906391 | 4906391 | 5097012.5 |  | 511.5 | 974 | 5098498 | 0.034 | 182580 | 173400 | 173400 | 9180 |  | 50 | 昌平
2012-11-29 | 项目部表,第44行 | XMF12-60 | 岳各庄居住东区1#地128公建 | 项目部 | 中铁建设集团有限公司 | 北京市 | 杨如林 | 北京和平芙蓉商贸有限公司 | 董宴春 | 否 |  | 1947790 | 3958320 |  |  | 0019537 | 2012-12-04 | 1773 |  | 完工 | 0.03 | 177183.3 | 177183 | 177183 | 0 | 4929108.8 | 4929108.8 | 4679800 | 4679800 | 79.24% | 3570320.71 | 3570320.71 | 3905909.71 |  |  |  | 3905909.71 | 0.034 | 167589.6992 | 167589 | 167589 | 0
2013-01-10 | 项目部表,第45行 | XMF13-01 | 北池子大街35号院翻改建 | 项目部 | 北京城建亚泰建设集团有限公司 | 北京市 | 霍林宝 | 中国人民解放军61159部队后勤部 | 霍林宝 | 否 |  | 1973264 | 1837947 |  |  | 0007311 | 2013-07-06 | 1144 |  | 完工 | 0.036 | 137203.596 | 137204 | 137204 | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 39.36% | 1373403.7 | 1373403.7 | 1424403.7 |  |  |  | 1424403.7 | 0.034 | 51000 | 51000 | 51000 | 0 |  | 20 | 亦庄
2013-01-23 | 项目部表,第46行 | XMF13-04 | 61886部队食堂及文体活动用房 | 项目部 | 中国人名解放军61886部队后勤部 | 北京市 | 霍林宝 | 中国人民解放军61886部队后勤部 | 霍林宝 | 否 |  | 478942 | 19643 |  |  | 0007312 | 2013-07-16 | 144 |  | 完工 | 0.036 | 17949.06 | 17831 | 17831 | 118.06 | 498585 | 498585 | 473655 | 473655 | 95% | 450000 | 450000 | 466952 |  |  |  | 466952 | 0.034 | 16951.89 | 16952 | 16952 | 0 |  | 6 | 亦庄
2013-01-20 | 项目部表,第47行 | XMF13-05 | 平谷金海湖小镇定向安置房 | 项目部 | 首创嘉铭新城镇投资发展有限公司 | 北京市 | 王娜 | 北京嘉世弘商贸有限公司 | 韩魁 | 否 |  | 5145173.21 |  |  |  | 0007306 | 2013-06-28 | 1544 |  | 完工 | 0.03 | 154355.1963 | 154355 | 154355 | 0 | 4112000 | 4112000 | 4112000 | 4112000 | 79.92% | 3963512.81 | 3963512.81 | 4103320.81 |  |  |  | 4103320.81 | 0.034 | 139808 | 139806 | 139806 | 0 |  | 75 | 大兴
2013-01-25 | 项目部表,第48行 | XMF13-06 | 广安门铁路住宅小区工程 | 项目部 | 中铁建工集团有限公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 5903500 |  |  |  | 0027651 | 2013-03-28 | 1772 |  | 完工 | 0.04 | 236140 | 236140 | 236140 | 0 | 5400000 | 5400000 | 4000000 | 4000000 | 67.76% | 2706499.32 | 2706499.32 | 3999943.58 |  |  |  | 3999943.58 | 0.034 | 183600 | 183600 | 183600 | 0 |  | 74 | 亦庄
2013-01-20 | 项目部表,第49行 | XMF13-07 | 国隆府综合楼玻璃幕墙工程 | 项目部 | 河北国隆房地产开发有限公司 | 河北省 | 王胜来 | 廊坊祖寺千首门窗公司 | 王胜来 | 异地交税 |  | 8338455 | 1516000 |  |  | 9061363 | 2013-10-22 | 2502 |  | 完工 | 0.03 | 295633.65 | 295634 | 295634 | 0 | 4000000 | 4000000 | 6000000 | 6000000 | 60.89% | 2634546 | 2634546 | 4265306 |  |  |  | 4265306 |  | 0 |  |  | 0 |  | 75 | 亦庄
2013-01-25 | 项目部表,第50行 | XMF13-08 | 4#生物研发楼等三项 | 项目部 | 北京中关村生命科学园发展有限责任公司 | 北京市 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 否 |  | 1707600 |  |  |  | 0027654 | 2013-04-02 | 513 |  | 完工 | 0.03 | 51228 | 51228 | 51228 | 0 | 1536840 | 1536840 | 1536840 | 1536840 | 90% | 1484089.7 | 1484089.7 | 1536342.7 |  |  |  | 1536342.7 | 0.034 | 52252.56 | 52253 | 52253 | 0
2013-01-29 | 项目部表,第51行 | XMF13-09 | 广安门铁路住宅小区B段 | 项目部 | 中铁电气化局集团北京建筑工程有限公司广安门项目 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 3171737 |  |  |  | 0027652 | 2013-03-28 | 952 |  | 完工 | 0.04 | 126869.48 | 126870 | 126870 | 0 | 3000000 | 3000000 | 3000000 | 3000000 | 94.59% | 2209075.2 | 2209075.2 | 2947212.54 |  |  |  | 2947212.54 | 0.034 | 102000 | 102000 | 102000 | 0 |  | 40 | 亦庄
2013-01-30 | 项目部表,第52行 | XMF13-10 | 广安门铁路住宅小区A段 | 项目部 | 中扶建设有限责任公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 3688900 | 2437951.61 |  |  | 0027653 | 2013-03-28 | 1107 |  | 完工 | 0.04 | 245074.0644 | 245074 | 245074 | 0 | 4400000 | 4400000 | 4400000 | 4400000 | 71.82% | 3910369.07 | 3910369.07 | 4363087.07 |  |  |  | 4363087.07 | 0.034 | 149600 | 149600 | 149600 | 0 |  | 78 | 亦庄
2013-02-25 | 项目部表,第53行 | XMF13-11 | 来广营B2地块项目 | 项目部 | 北京方兴融创房地产开发有限公司 | 北京市 | 姚志刚 | 中盛泰和（北京）进出口有限公司 | 孙辉 | 否 |  | 10242431.93 |  |  |  | 0027643 | 2013-03-09 | 3073 |  | 完工 | 0.03 | 307272.9579 | 307273 | 307273 | 0 | 5355000 | 5355000 | 5355000 | 5355000 | 52.28% | 4746409.25 | 4746409.25 | 5006374.95 |  |  |  | 5006374.95 | 0.034 | 182070 | 182070 | 182070 | 0 |  | 150 | 管庄
2013-03-01 | 项目部表,第54行 | XMF13-12 | 新华联雅园一期工程 | 项目部 | 内蒙古新华联置业有限公司 | 内蒙古 | 金生文 | 北京长风幕墙装饰有限公司 | 李猛 | 异地交税 |  | 10182154.2 |  |  |  | 0027646 | 2013-03-18 | 3055 |  | 完工 | 0.03 | 305464.626 | 305465 | 305465 | 0 | 6658381.32 | 6658381.32 | 6658381.32 | 6658381.32 | 65.39% | 5550984.4 | 5550984.4 | 6656819.76 |  |  |  | 66566819.76 |  | 0 |  |  | 0 |  | 123 | 亦庄
2013-03-28 | 项目部表,第55行 | XMF13-13 | 北京国际文化贸易企业集散中心 | 项目部 | 北京歌华美创空港置业有限公司 | 北京市 | 刘乃适 | 北京中适广发智能门有限公司 | 刘乃适 | 否 |  | 35281540.55 | 1087789.19 |  |  | 0026991 | 2013-05-16 | 10585 |  | 完工 | 0.03 | 1091079.8922 | 1064887 | 1064887 | 26192.8922 | 25050105 | 25050105 | 25050105 | 25050105 | 68.88% | 23540714.64 | 23540714.64 | 25042419.64 |  |  |  | 25042419.64 | 0.034 | 851703.57 | 851705 | 851705 | 0 |  | 180 | 管庄
2013-03-28 | 项目部表,第56行 | XMF13-14 | 京昌高科技信息产业园3#厂房 | 项目部 | 北京市昌平一建建筑有限责任公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 1995000 |  |  |  | 0026999 | 2013-06-04 | 599 |  |  | 0.036 | 71820 |  |  | 71820 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0 |  | 26 | 管庄
2013-03-28 | 项目部表,第57行 | XMF13-15 | 61599部队清河经济适用住房工程 | 项目部 | 中建交通建设集团有限公司 | 北京市 | 吴荣 | 北京佳盛杰瑞商贸有限公司 | 季福成 | 否 |  | 9000000 |  |  |  | 0027658 | 2013-04-20 | 2700 |  | 完工 | 0.03 | 270000 | 210000 | 210000 | 60000 | 9000000 | 9000000 | 4800000 | 4800000 | 53.33% | 2571030.19 | 2571030.19 | 4800000 |  |  |  | 4800000 | 0.034 | 306000 | 306000 | 306000 | 0 |  | 10 | 管庄
2013-04-13 | 项目部表,第58行 | XMF13-16 | 解放军总医院研究大楼改造 | 项目部 | 中国人民解放军总医院第一附属医院 | 北京市 | 付仁福 | 北京富恒兴达装饰工程有限公司 | 付仁福 | 否 |  | 2600000 |  |  |  | 0027659 | 2013-04-25 | 780 |  | 完工 | 0.036 | 93600 | 93600 | 93600 | 0 | 2894471 | 2894471 | 2894471 | 2894471 | 111.3% | 2705613.68 | 2705613.68 | 2804025.68 |  |  |  | 2804025.68 | 0.034 | 98412.014 | 98412 | 98412 | 0
2013-04-01 | 项目部表,第59行 | XMF13-17 | 朝阳区东坝驹子房农民安置房F区 | 项目部 | 北京市朝阳城市建设综合开发公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 12491680 |  |  |  | 0007301 | 2013-06-04 | 3748 |  | 正常进行 | 0.03 | 374750.4 | 374750 | 374750 | 0 | 11200000 | 11200000 | 11200000 | 11200000 | 89.66% | 10579700.51 | 10579700.51 | 11184000.51 |  |  |  | 11184000.51 | 0.034 | 380800 | 380800 | 380800 | 0 |  | 145 | 三河
2013-04-01 | 项目部表,第60行 | XMF13-18 | 华北运转中心项目仓储物流及附属设施 | 项目部 | 北京京都圆通速递有限公司 | 北京市 | 王治国 | 北京和平银泰装饰有限公司 | 王松琴 | 否 |  | 1195559 | 934441 |  |  | 0026984 | 2013-05-16 | 359 |  | 完工 | 0.036 | 76680 | 76680 | 76680 | 0 | 2130000 | 2130000 | 2023500 | 2023500 | 95% | 1200000 | 1200000 | 1971374.8 |  |  |  | 1971374.8 | 0.034 | 72420 | 72420 | 72420 | 0 |  | 16 | 亦庄
2013-05-02 | 项目部表,第61行 | XMF13-19 | 西郊机场西区12#住宅楼工程 | 项目部 | 空军第一建筑安装工程总队 | 北京市 | 赵长亮 | 北京雄博兴业装饰设计有限公司 | 李国兵 | 否 |  | 1258749 |  |  |  | 0026982 | 2013-05-16 | 378 |  | 完工 | 0.036 | 45314.964 | 45315 | 45315 | 0 | 1052000 | 1052000 | 1052000 | 1052000 | 83.58% | 1009286 | 1009286 | 1045054 |  |  |  | 1045054 | 0.034 | 35768 | 35768 | 35768 | 0
2013-05-01 | 项目部表,第62行 | XMF13-20 | 厦门高崎国际机场T4航站楼 | 项目部 | 森特士兴集团股份有限公司 | 福建厦门 | 杨如林 | 北京和平芙蓉商贸有限公司 | 董宴春 | 否 |  | 2894611 |  |  |  | 0007313 | 2013-07-08 | 869 |  | 完工 | 0.036 | 104205.996 | 104206 | 104206 | 0 | 1528383.3 | 1528383.3 | 1528383.3 | 1528383.3 | 52.8% | 1476000 | 1476000 | 1527965 |  |  |  | 1527965 | 0.034 | 51965.0322 | 51965 | 51965 | 0
2013-05-01 | 项目部表,第63行 | XMF13-21 | 西郊机场西区10#住宅楼工程 | 项目部 | 95959部队 | 北京市 | 赵长亮 | 北京雄博兴业装饰设计有限公司 | 李国兵 | 否 |  | 1691837.01 |  |  |  | 0007303 | 2013-06-06 | 508 |  | 完工 | 0.036 | 60906.1324 | 60906 | 60906 | 0 | 1892244 | 1892244 | 1892244 | 1892244 | 111.8% | 1729640 | 1729640 | 1796006 |  |  |  | 1796006 | 0.034 | 64336.296 | 64336 | 64336 | 0 |  | 15 | 京顺
2013-05-18 | 项目部表,第64行 | XMF13-22 | 红星国际广场3#地地块 | 项目部 | 天津市华运商贸物业有限公司 | 天津市 | 闫禄章 | 北京奥维尔建筑材料销售有限公司 | 闫禄章 | 异地交税 |  | 6498959 | [7 empty] | 完工 | 0.03 | 194968.77 | 194969 | 194969 | 0 | 5165199.2 | 5165199.2 | 4941545.5 | 4941545.5 | 76.04% | 4612419.2 | 4612419.2 | 4934017.45 |  |  |  | 4934017.45 | 0.0374 | 193178.4501 | 193178.45 | 193178.45 | 8e-05 |  | 80 | 管庄
2013-05-23 | 项目部表,第65行 | XMF13-23 | 衙门口居住公建A1地块 | 项目部 | 北京天石基业房地产开发有限公司 | 北京市 | 李智勇 | 北京通联门窗有限公司 | 吕松岩 | 否 |  | 6000000 | 2023835.04 |  |  | 0026998 | 2013-05-30 | 1800 |  | 完工 | 0.03 | 240715.0512 | 240715 | 240715 | 0 | 8023835.04 | 8023835.04 | 8023835.04 | 8023835.04 | 100% | 7479804.75 | 7479804.75 | 7749964.75 |  |  |  | 7749964.75 | 0.034 | 272810.3914 | 272810 | 272810 | 0
2013-06-13 | 项目部表,第66行 | XMF13-24 | 朝阳区十八里店周庄三期 | 项目部 | 北京市朝阳田华建筑集团公司/北京大洋房地产开发有限够告诉你 | 北京市 | 柯善波 | 北京福宏杰幕墙门窗技术有限公司 | 柯善波 | 否 |  | 15283442.58 | 1303649.56 |  |  | 0007305 | 2013-06-14 | 4586 |  | 正常进行 | 0.04 | 658269.0874 | 658269 | 658269 | 0 | 14335455.08 | 14335455.08 | 13433095.44 | 13433095.44 | 80.99% | 13740016.29 | 13740016.29 | 14227421.29 |  |  |  | 14227421.29 | 0.034 | 487405.4727 | 487405 | 487405 | 0.47272
2013-06-14 | 项目部表,第67行 | XMF13-25 | 北京市平谷检察院办案和专业技术房 | 项目部 | 北京诚通新新建设有限公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 1712229.71 |  |  |  | 0061064 | 2013-08-09 | 514 |  | 正常进行 | 0.036 | 61640.2696 | 61640 | 61640 | 0 |  |  | 0 | 0 | 0% | [7 empty] | 0.034 | 0 |  |  |  |  | 19 | 三河
2013-06-18 | 项目部表,第68行 | XMF13-26 | 铁科院永丰基地扩建项目 | 项目部 | 中铁电气化局集团北京建筑工程有限公司 | 北京市 | 何金才 | 徐水县鸿飞橡塑制品有限公司 | 周俊才 | 否 |  | 7389748 | 1116572 |  |  | 0007318 | 2013-07-29 | 2217 |  | 正常进行 | 0.03 | 255189.6 | 255192.27 | 255191.27 | 0 | 8506320 | 8506320 | 8506320 | 8506320 | 100% | 8036530.95 | 8036530.95 | 8505439.07 |  |  |  | 8505439.07 | 0.034 | 289214.88 | 289214 | 289214 | 0 |  | 50 | 管庄
2013-07-01 | 项目部表,第69行 | XMF13-27 | 国贸世纪公寓样板间外墙工程 | 项目部 | 中国国际贸易中心有限公司 | 北京市 | 柯秋惠 | 北京宇光装饰有限公司 | 柯秋惠 | 否 |  | 205000 | [7 empty] | 正常进行 | 0.036 | 7380 | 7380 | 7380 | 0 | 194750 | 194750 | 194750 | 194750 | 95% | 155447.2 | 155447.2 | 192069.2 |  |  |  | 192069.2 | 0.034 | 6621.5 | 6622 | 6622 | 0
2013-07-02 | 项目部表,第70行 | XMF13-28 | 利生大厦综合办公楼项目外立面 | 项目部 |  | 北京市 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 否 |  | 5287718 |  |  |  | 0061074 | 2013-09-14 | 1587 |  | 正常进行 | 0.03 | 158631.54 |  |  | 158631.54 |  |  | 0 | 0 | 0% | [7 empty] | 0.034 | 0 |  |  |  |  | 15 | 管庄
2013-07-04 | 项目部表,第71行 | XMF13-29 | 航天长征睿特科技天津生产基地 | 项目部 | 北京航天万源建筑工程有限责任公司 | 天津市 | 李玉朝 | 北京若愚装饰有限公司 | 杨书芳 | 异地交税 |  | 2440063.9 | [7 empty] | 正常进行 | 0.046 | 112242.9394 | 112243.75 | 112243.75 | 0 | 2352756.32 | 2352756.32 | 1952051.12 | 1952051.12 | 80% | 1554257.75 | 1554257.75 | 1936975.93 |  |  |  | 1936975.93 | 0.0374 | 87993.0864 | 87993.09 | 87993.09 | 0
2013-07-15 | 项目部表,第72行 | XMF13-30 | 96819部队工程 | 项目部 | 中国新兴建设开发总公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 1457017.94 |  |  |  | 0061065 | 2013-08-13 | 438 |  | 正常进行 | 0.036 | 52452.6458 | 52453 | 52453 | 0 | 1400000 | 1400000 | 1400000 | 1400000 | 96.09% | 1335000 | 1335000 | 1384348 |  |  |  | 1384348 | 0.034 | 47600 | 47600 | 47600 | 0
2013-07-17 | 项目部表,第73行 | XMF13-31 | 中国国际贸易中心二座幕墙工程 | 项目部 | 中国国际贸易中心股份有限公司二期物业中心 | 北京市 | 柯秋惠 | 北京宇光装饰有限公司 | 柯秋惠 | 否 |  | 190000 |  |  |  | 0061068 | 2013-08-29 | 57 |  | 正常进行 | 0.036 | 6840 |  |  | 6840 | 180500 | 180500 | 57000 | 57000 | 30% |  |  | 50000 |  |  |  | 50000 | 0.034 | 6137 |  |  | 6137
2013-07-29 | 项目部表,第74行 | XMF13-32 | 密云县穆家岭希望一期3#地 | 项目部 | 北京华润希望发展有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 2768475 |  |  |  | 0064207 | 2013-09-04 | 831 |  | 完工 | 0.036 | 99665.1 | 99665 | 99665 | 0 | 2353204 | 2353204 | 2353204 | 2353204 | 85% | 2021228.99 | 2021228.99 | 2338304.99 |  |  |  | 2338304.99 | 0.034 | 80008.936 | 80009 | 80009 | 0
2013-07-29 | 项目部表,第75行 | XMF13-33 | 大兴北臧村镇居住及配套项目 | 项目部 | 北京博大经开建设有限公司 | 北京市 | 张永强 | 北京泰顺源装饰装潢有限公司 | 张永强 | 异地交税 |  | 19543207.13 |  |  |  | 0061071 | 2013-09-05 | 5863 |  | 正常进行 | 0.03 | 586296.2139 | 586297 | 586297 | 0 | 12820000 | 12820000 | 7790000 | 7790000 | 39.86% | 10117250.52 | 10117250.52 | 10577625.82 |  |  |  | 10577625.82 | 0.034 | 435880 | 232900 | 232900 |  |  | 96 | 管庄
2013-08-08 | 项目部表,第76行 | XMF13-34 | 天津东疆港瞰海轩工程 | 项目部 |  | 天津市 | 王培俊 | 北京玉林强钢化玻璃有限公司 | 王培俊 | 异地交税 |  | 8061172 | [7 empty] | 正常进行 | 0.03 | 241835.16 | 240000 | 240000 | 1835.16 | 1600000 | 1600000 | 1040000 | 1040000 | 12.9% | 1002259 | 1002259 | 1039549 |  |  |  | 1039549 | 0.0374 | 59840 | 59840 | 59840 | 0 |  | 105 | 管庄
2013-08-01 | 项目部表,第77行 | XMF13-35 | 红星国际广场3#地A1楼铝合金门窗 | 项目部 | 天津市华运商贸物业有限公司 | 天津市 | 闫禄章 | 北京奥维尔建筑材料销售有限公司 | 闫禄章 | 异地交税 |  | 3427568 | [7 empty] | 正常进行 | 0.03 | 102827.04 | 102827 | 102827 | 0 | 2742054.4 | 2742054.4 | 2576919.68 | 2576919.68 | 75.18% | 2316496.25 | 2316496.25 | 2572434.86 |  |  |  | 2572434.86 | 0.0374 | 102552.8346 | 102552.83 | 102552.83 | 0.00456 |  | 42 | 管庄
2013-08-10 | 项目部表,第78行 | XMF13-36 | 温泉公寓B型公寓一期外立面 | 项目部 | 北京春晖园文化娱乐有限责任公司 | 北京市 | 纪树军 | 北京中建润泽建筑工程有限公司 | 李邦海 | 否 |  | 2823828.2 |  |  |  | 0061067 | 2013-08-26 | 848 |  | 正常进行 | 0.03 | 84714.846 | 84715 | 84715 | 0 | 2034096.63 | 2034096.63 | 2034096.63 | 2034096.63 | 72.03% | 1735922.11 | 1735922.11 | 1805082.11 |  |  |  | 1805082.11 | 0.034 | 69159.2854 | 69160 | 69160 | 0 |  | 6 | 管庄
2013-08-20 | 项目部表,第79行 | XMF13-37 | 新宁波站改建工程 | 项目部 | 中铁建设集团有限公司宁波铁路枢纽工程项目经理部 | 浙江宁波 | 杨如林 | 北京和平芙蓉商贸有限公司 | 董宴春 | 异地交税 |  | 17411600 | 14846 |  |  | 0061070 | 2013-09-04 | 5224 |  | 正常进行 | 0.03 | 522793.38 | 522348 | 522348 | 445.38 | 17426446 | 17426446 | 11880000 | 11880000 | 68.17% | 11232076.7 | 11232076.7 | 11735031.74 |  |  |  | 11735031.74 |  | 0 |  |  | 0
2013-08-25 | 项目部表,第80行 | XMF13-38 | 国网智能电网研究院倒班宿舍楼 | 项目部 | 中铁建设集团有限公司 | 北京市 | 杨如林 | 北京和平芙蓉商贸有限公司 | 董宴春 | 否 |  | 407310.98 |  |  |  | 0061073 | 2013-09-06 | 123 |  | 正常进行 | 0.036 | 14663.1953 | 14663 | 14663 | 0 | 407310.98 | 407310.98 | 350000 | 350000 | 85.93% | 300000 | 300000 | 313849 |  |  |  | 313849 | 0.034 | 13848.5733 | 13849 | 13849 | 0
2013-09-02 | 项目部表,第81行 | XMF13-39 | 锋创科技园4#研发办公楼 | 项目部 | 锋创科技发展（北京）有限公司 | 北京市 | 苏洪波 | 北京嘉世弘商贸有限公司 | 韩魁 | 否 |  | 8700000 | 7411961 |  |  | 0245333 | 2014-01-08 | 2610 |  | 正常进行 | 0.03 | 483358.83 | 476853 | 476853 | 6505.83 | 10308167.64 | 10308167.64 | 9343700.05 | 9343700.05 | 57.99% | 7420626.79 | 7420626.79 | 8252263.79 |  |  |  | 8252263.79 | 0.034 | 350477.6998 | 350477 | 350477 | 0 |  | 90 | 管庄
2013-09-05 | 项目部表,第82行 | XMF13-40 | 望海楼南侧 | 项目部 | 北京德海鸿业投资有限公司 | 北京市 | 纪树军 | 北京中建润泽建筑工程有限公司 | 李邦海 | 否 |  | 360000 |  |  |  | 0061075 | 2013-09-23 | 108 |  | 完工 | 0.036 | 12960 | 12960 | 12960 | 0 | 251827 | 251827 | 250827 | 250827 | 69.67% | 239535.1 | 239535.1 | 248097.1 |  |  |  | 248097.1 | 0.034 | 8562.118 | 8562 | 8562 | 0
2013-11-10 | 项目部表,第83行 | XMF13-41 | 欧逸丽庭二期北标段项目 | 项目部 | 三河成功房地产开发有限公司/中建二局第一建筑工程有限公司 | 河北燕郊 | 王军 | 北京军建凯达幕墙装饰有限公司 | 秦存国 | 异地交税 |  | 20420000 |  |  |  | 9061373 | 2013-11-26 | 6126 |  | 正常进行 | 0.03 | 612600 | 612600.5 | 612600.5 | 0 | 7357840.36 | 7357840.36 | 7357840.36 | 7357840.36 | 36.03% | 7006009.7 | 7006009.7 | 7147414.33 | 121 | 956 | 1825 | 7150316.33 | 0.0356 | 261939.1168 |  |  | 0
2013-09-15 | 项目部表,第84行 | XMF13-42 | 成功（中国）大广场休闲娱乐中心 | 项目部 | 成功（中国）大广场有限公司/中国建筑第二工程局有限公司 | 河北燕郊 | 王军 | 北京军建凯达幕墙装饰有限公司 | 秦存国 | 异地交税 |  | 26077738.8 |  |  |  | 9061374 | 2013-11-26 | 7824 |  | 正常进行 | 0.03 | 782332.164 | 6047 | 6047 | 776285.164 |  |  | 0 | 0 | [8 empty] | 0.0356 | 0 |  |  |  |  | 180 | 管庄
2013-09-18 | 项目部表,第85行 | XMF13-43 | 华远大厦维修项目 | 项目部 | 北京市华远集团有限公司 | 北京市 | 金生文 | 北京长风幕墙装饰有限公司 | 李猛 | 否 |  | 937580 |  |  |  | 0061077 | 2013-09-30 | 282 |  | 正常进行 | 0.036 | 33752.88 | 33753 | 33753 | 0 | 589567.2 | 589567.2 | 589567.2 | 589567.2 | 62.88% | 562960 | 562960 | 583005 |  |  |  | 583005 | 0.034 | 20045.2848 | 20045 | 20045 | 0
2013-10-10 | 项目部表,第86行 | XMF13-44 | 香河鸿坤理想城阳光项目 | 项目部 | 香河县鸿坤房地产开发有限公司 | 河北香河 | 冯国亮 | 三河市益吉装饰工程有限公司 | 冯国亮 | 否 |  | 7763574.66 |  |  |  | 0245329 | 2013-12-19 | 2330 |  | 正常进行 | 0.03 | 232907.2398 | 92979 | 92979 | 139928.2398 | 4906233 | 4906233 | 3423677 | 3423677 | 44.1% | 3263646.19 | 3263646.19 | 3414292.42 |  |  |  | 3414292.42 | 0.034 | 166811.922 | 87101 | 87101 |  |  | 100 | 三河
2013-10-15 | 项目部表,第87行 | XMF13-45 | 1#楼生物技术研发中心项目幕墙工程 | 项目部 | 北京城建七建设工程有限公司 | 北京市 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 否 |  | 11700792.69 |  |  |  | 1245398 | 2014-05-23 | 4111 |  | 正常进行 | 0.03 | 351023.7807 | 351024 | 351024 | 0 | 5874521 | 5874521 | 5874521 | 5874521 | 50.21% | 5402150.13 | 5402150.13 | 5800083.13 |  |  |  | 5800083.13 | 0.034 | 199733.714 | 199733 | 199733 | 0 |  | 85 | 管庄
2013-10-19 | 项目部表,第88行 | XMF13-46 | A1厂房等8项-B1研发楼 | 项目部 | 北京港荣食品有限公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 3443591.39 |  |  |  | 1251028 | 2014-04-07 | 1034 |  | 正常进行 | 0.036 | 123969.29 | 123969 | 123969 | 0 | 2421795.42 | 2421795.42 | 2421795.42 | 2421795.42 | 70.33% | 2312874.58 | 2312874.58 | 2359931.39 |  |  | 10613 | 2370544.39 | 0.034 | 82341.0443 | 82341 | 82341 | 0 |  | 52 | 三河
2013-10-05 | 项目部表,第89行 | XMF13-47 | 数据技术研发中心建设项目6#楼 | 项目部 | 汇天网络科技有限公司 | 北京市 | 李智勇 | 北京通联门窗有限公司 | 吕松岩 | 否 |  | 14920000 | 53188404.71 |  |  | 1251034 | 2014-04-10 | 4476 |  | 正常进行 | 0.025 | 1702710.1178 | 1103347 | 1103347 | 599363.1178 | 15000000 | 15000000 | 14978500 | 14978500 | 21.99% | 11787002.56 | 11787002.56 | 12097000.56 |  |  |  | 12097000.56 | 0.034 | 510000 | 510000 | 510000 | 0 |  | 210 | 管庄
2013-10-15 | 项目部表,第90行 | XMF13-48 | 研发办公楼D座等16项 | 项目部 | 中国新兴建设开发总公司 | 北京市 | 曲刚 | 北京京业正通建筑材料有限责任公司 | 王艳 | 是 |  | 126591039.39 | [7 empty] | 正常进行 | 0.02 | 2531820.7878 | 2317283.86 | 2317283.86 | 214536.9278 | 43167474.46 | 43167474.46 | 43167473.98 | 43167473.98 | 34.1% | 36009565.64 | 36009565.64 | 40907590.87 |  |  |  | 40907590.87 | 0.0336 | 1450427.1419 |  |  |  |  | 530 | 管庄
2013-10-18 | 项目部表,第91行 | XMF13-49 | 天津红星国际广场3#地A2-A4楼 | 项目部 | 天津市华运商贸物业有限公司 | 天津市 | 闫禄章 | 北京奥维尔建筑材料销售有限公司 | 闫禄章 | 异地交税 |  | 5992383 | [7 empty] | 正常进行 | 0.03 | 179771.49 | 129771 | 129771 | 50000.49 | 4194668 | 4194668 | 4194668 | 4194668 | 70% | 3543290 | 3543290 | 3845489.24 |  |  |  | 3845489.24 | 0.0374 | 156880.5832 |  |  |  |  | 66 | 管庄
2013-11-01 | 项目部表,第92行 | XMF13-50 | 金宝花园 | 项目部 | 北京金宝房地产开发有限公司 | 北京市 | 韩魁 | 北京嘉世弘商贸有限公司 | 韩魁 | 否 |  | 3117195.98 |  |  |  | 0245330 | 2013-12-19 | 936 |  | 正常进行 | 0.036 | 112219.0553 | 112219 | 112219 | 0 | 1555000 | 1555000 | 1520000 | 1520000 | 48.76% | 1449499.64 | 1449499.64 | 1502369.64 |  |  |  | 1502369.64 | 0.034 | 52870 | 52870 | 52870 | 0 |  | 35 | 大兴
2013-11-21 | 项目部表,第93行 | XMF13-51 | 大兴定向安置房（榆垡） | 项目部 | 北京万兴建筑集团有限公司 | 北京市 | 孙磊 | 北京红星日晟门窗厂 | 李书玉 | 否 |  | 5811890 |  |  |  | 0245328 | 2013-11-21 | 1744 |  | 完工 | 0.04 | 232475.6 | 232476 | 232476 | 0 | 2200000 | 2200000 | 2200000 | 2200000 | 37.85% | 1623974 | 1623974 | 1698774 |  |  |  | 1698774 | 0.034 | 74800 | 74800 | 74800 | 0
2013-11-05 | 项目部表,第94行 | XMF13-52 | 橡树湾售楼样板间 | 项目部 | 北京优高雅装饰工程有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 76467 | 479 |  |  | 0245339 | 2014-01-18 | 23 |  | 完工 | 0.036 | 2770.056 | 2753 | 2753 | 17.056 | 76946 | 76946 | 54000 | 54000 | 70.18% | 50000 | 50000 | 52616 |  |  |  | 52616 | 0.034 | 2616.164 | 2616 | 2616 | 0
2013-11-14 | 项目部表,第95行 | XMF13-53 | 肽谷生命科学园1-2期 | 项目部 | 固安肽谷药业科技有限公司 | 河北固安 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 异地交税 |  | 3058486 |  |  |  | 9061371 | 2013-11-18 | 918 |  | 完工 | 0.036 | 110105.496 | 110105.36 | 110105.36 | 0 | 2140940.2 | 2140940.2 | 2140940.2 | 2140940.2 | 70% | 1955643.64 | 1955643.64 | 2022412.17 | 714 | 3016.5 | 3827 | 2029969.67 |  | 0 |  |  |  |  | 30 | 管庄
2013-11-18 | 项目部表,第96行 | XMF13-54 | 门头沟项目B区铝合金门窗及百叶 | 项目部 | 华润置地发展（北京）有限公司/中天建设集团有限公司 | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 12067070 |  |  |  | 0446167 | 2014-06-05 | 3621 |  | 正常进行 | 0.03 | 362012.1 |  |  | 362012.1 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0 |  | 140 | 大厂
2013-12-01 | 项目部表,第97行 | XMF13-55 | 德州康博公馆一期一标段工程 | 项目部 | 青建集团股份公司 | 山东德州 | 李金光 | 北京丰益宏业装饰有限公司 | 李金光 | 异地交税 |  | 11000000 |  |  |  | 0245321 | 2013-12-06 | 3300 |  | 正常进行 | 0.03 | 330000 | 330000 | 330000 | 0 | 5500000 | 5500000 | 5000000 | 5000000 | 45.45% | 4680000 | 4680000 | 4916450 |  |  |  | 4916450 |  | 0 |  |  | 0 |  | 120 | 昌平
2013-12-01 | 项目部表,第98行 | XMF13-56 | 房山长沟镇改造一期 | 项目部 | 中国新兴建设开发总公司 | 北京市 | 付仁福 | 北京富恒兴达装饰工程有限公司 | 付仁福 | 否 |  | 924545 |  |  |  | 0245327 | 2013-12-17 | 278 |  | 正常进行 | 0.03 | 27736.35 | 2200 | 2200 | 25536.35 | 300000 | 300000 | 300000 | 300000 | 32.45% | 202490 | 202490 | 219322.49 |  |  | 2490 | 221812.49 | 0.034 | 10200 | 10200 | 10200 | 0 |  | 7 | 亦庄
2013-12-10 | 项目部表,第99行 | XMF13-57 | 合肥南站 | 项目部 | 中铁建设集团有限公司 | 安徽合肥 | 颜自成 | 杭州创基建筑装饰工程有限公司 | 王艳 | 异地交税 |  | 19413696.16 |  |  |  | 1251031 | 2014-04-10 | 5825 |  | 正常进行 | 0.03 | 582410.8848 | 582411 | 582411 | 0 | 11410745 | 11410745 | 12320000 | 12320000 | 63.46% | 11478428.55 | 11478428.55 | 11478428.55 |  |  |  | 11478428.55 |  |  |  |  | 0
2013-12-18 | 项目部表,第100行 | XMF13-58 | 华茂嘉园住宅小区隔热 | 项目部 | 江苏金月房地产集团有限公司 |  | 马泽永 | 天津市百环工贸有限公司 | 王同利 |  |  | 8060000 | [7 empty] | 正常进行 | 0.03 | 241800 | 241800 | 241800 | 0 |  |  | 3057158 | 3057158 | 37.93% | 2765096.52 | 2765096.52 | 2765096.52 |  |  |  | 2765096.52 |  |  |  |  | 0 |  | 104 | 三河
2013-12-18 | 项目部表,第101行 | XMF13-59 | 5#生物研发楼外幕墙工程 | 项目部 | 北京中关村生命科学院园发展有限责任公司 | 北京市 | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | 否 |  | 229276 |  |  |  | 0446161 | 2014-05-23 | 69 |  | 完工 | 0.03 | 6878.28 |  |  | 6878.28 | 91710.76 | 91710.76 | 91710.76 | 91710.76 | 40% | 60349 | 60349 | 66158 |  |  |  | 66158 | 0.034 | 3118.1658 | 3118 | 3118 | 0 |  | 2 | 管庄
2013-12-20 | 项目部表,第102行 | XMF13-60 | 总政机关黄寺礼堂 | 项目部 | 中国人民解放军总政治部机关营建办公室 | 北京市 | 李玉朝 | 北京若愚装饰有限公司 | 杨书芳 | 否 |  | 330000 |  |  |  | 0245332 | 2013-12-25 | 99 |  | 完工 | 0.036 | 11880 | 3405.5 | 3405.5 | 8474.5 | 180000 | 180000 | 180000 | 180000 | 54.55% | 170720 | 170720 | 176120 |  | 720 |  | 176840 | 0.034 | 6120 | 6120 | 6120 | 0 |  | 5 | 昌平
2014-01-01 | 项目部表,第103行 | XMF14-01 | 贵阳北站 | 项目部 | 中铁建设集团有限公司贵阳北站项目经理部 | 贵州省贵阳市 | 王江军 | 杭州蓝博凯盾防火门有限公司 | 王江军 | 异地交税 |  | 61225227 |  |  |  | 1251022 | 2014-02-27 | 18368 |  | 正常进行 | 0.025 | 1530630.675 | 790000 | 790000 | 740630.675 | 28124956.18 | 28124956.18 | 19687469.33 | 19687469.33 | 32.16% | 14697501.28 | 14697501.28 | 17777554.56 |  |  |  | 17777554.56 | 0.0356 | 1001248.44 | [5 empty] | 亦庄
2014-01-01 | 项目部表,第104行 | XMF14-02 | 3829玻璃石材幕墙及断桥铝合金 | 项目部 | 61195部队后勤部管理处财务科 | 北京市 | 霍林宝 | 中国人民解放军61159部队后勤部 | 霍林宝 | 否 |  | 14355608.07 |  |  |  | 1251023 | 2014-03-05 | 4307 |  | 正常进行 | 0.032 | 459379.4582 | 459379 | 459379 | 0 | 10766705.58 | 10766705.58 | 10766705.58 | 10766705.58 | 75% | 8237236.89 | 8237236.89 | 10005119.24 |  |  |  | 10005119.24 | 0.034 | 366067.9897 | 366068 | 366068 | 0
2014-01-01 | 项目部表,第105行 | XMF14-03 | 解放军302医院感染综合楼 | 项目部 | 中国人民解放军第三〇二医院 | 北京市 | 邵幸来 | [12 empty] | 正常进行 |  | 0 |  |  | 0 |  |  | 0 | 0 | [9 empty] | 0
2014-01-01 | 项目部表,第106行 | XMF14-04 | 北京实创科技园开发建设股份有限公司 | 项目部 | 中集建设集团有限公司 | 北京市 | 金生文 | 北京长风幕墙装饰有限公司 | 李猛 | 否 |  | 42615176.35 | [7 empty] | 正常进行 | 0.03 | 1278455.2905 | 800000 | 800000 | 478455.2905 | 17886113.5 | 17886113.5 | 17886113.5 | 17886113.5 | 41.97% | 16222938.1 | 16222938.1 | 17003848.52 |  |  |  | 17003848.52 | 0.034 | 608127.859 | 608128 | 608128 | 0 |  | 150 | 亦庄
2014-03-01 | 项目部表,第107行 | XMF14-06 | 北京嘉里中心翻装项目办公楼 | 项目部 | 北京嘉奥房地产开发有限公司 | 北京市 | 柯秋惠 | 北京宇光装饰有限公司 | 柯秋惠 | 否 |  | 261648.41 |  |  |  | 1251026 | 2014-03-26 | 79 |  | 正常进行 | 0.036 | 9419.3428 | 9419 | 9419 | 0 | 248565.99 | 248565.99 | 248565.99 | 248565.99 | 95% | 109977 | 109977 | 248518 |  |  |  | 248518 | 0.034 | 8451.2437 | 8541 | 8541 | 0
2014-03-01 | 项目部表,第108行 | XMF14-07 | 德州康博公馆一期2#工程 | 项目部 | 中天建设集团有限公司德厚分公司 | 山东德州 | 李金光 | 北京丰益宏业装饰有限公司 | 李金光 |  |  | 1054353.53 | [7 empty] | 正常进行 | 0.03 | 31630.6059 | 31631 | 31631 | 0 | 200000 | 200000 | 200000 | 200000 | 18.97% | 80000 | 80000 | 86800 |  |  |  | 86800 | 0.034 | 6800 | 6800 | 6800 | 0 |  | 15 | 昌平
2014-04-01 | 项目部表,第109行 | XMF14-08 | 北京联合大学第二教学楼 | 项目部 | 北京市第五建筑工程集团有限公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 1393840 | 853433.7 |  |  | 1245385 | 2014-05-04 | 419 |  | 正常进行 | 0.036 | 50178.24 | 50613 | 50613 | -434.76 | 1142434.71 | 1142434.71 | 1142434.71 | 1142434.71 | 50.84% | 932058.05 | 932058.05 | 972572.05 |  |  |  | 972572.05 | 0.034 | 38842.7801 | 38842 | 38842 | 0 |  | 20 | 三河
2014-04-01 | 项目部表,第110行 | XMF14-09 | 北京西红门兴海学校扩建项目 | 项目部 | 北京鸿坤伟业房地产开发有限公司 | 北京市 | 冯国亮 | 三河市益吉装饰工程有限公司 | 冯国亮 | 否 |  | 1470000 | [7 empty] | 正常进行 | 0.036 | 52920 |  |  | 52920 | 1176000.01 | 1176000 | 664033.28 | 664033.28 | 45.17% | 243938.24 | 243938.24 | 283922.24 |  |  |  | 283922.24 | 0.034 | 39984 | 39984 | 39984 | 0 |  | 1 | 三河
2014-04-16 | 项目部表,第111行 | XMF14-10 | 中国人民解放军96819部队综合管理楼 | 项目部 | 中国新兴建设开发总公司 | 北京市 | 马泽永 | 天津市百环工贸有限公司 | 王同利 | 否 |  | 1287679 | [7 empty] | 正常进行 | 0.036 | 46356.444 | 46356 | 46356 | 0 | 400000 | 400000 | 400000 | 400000 | 31.06% | 353418.72 | 353418.72 | 367018.72 |  |  |  | 367018.72 | 0.034 | 13600 | 13600 | 13600 | 0 |  | 20 | 三河
2014-04-18 | 项目部表,第112行 | XMF14-11 | 大兴京城高尔夫俱乐部 | 项目部 | 北京建工博海建设有限公司 | 北京市 | 孙超 | 北京海锐广告有限公司 | 孙超 | 否 |  | 420488.3 |  |  |  | 0446164 | 2014-05-30 | 127 |  | 正常进行 | 0.036 | 15137.5788 |  |  | 15137.5788 | 378000 | 378000 | 378000 | 378000 | 89.9% | 318684.49 | 318684.49 | 351536.49 |  |  |  | 351536.49 | 0.034 | 12852 | 12852 | 12852 | 0 |  | 5 | 三河
2014-04-15 | 项目部表,第113行 | XMF14-12 | 援肯尼亚卡通都医院 | 项目部 |  |  | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 |  |  | 1414102.49 | [7 empty] | 正常进行 | 0.036 | 50907.6896 | 50908 | 50908 | 0 |  |  | 0 | 0 | [9 empty] | 0 |  |  | 0 |  | 15 | 管庄
2014-05-01 | 项目部表,第114行 | XMF14-13 | 天津东疆港瞰海轩工程 | 项目部 | 浙江宝业建设集团有限公司 | 天津市 | 王培俊 | 北京玉林强钢化玻璃有限公司 | 王培俊 | 异地交税 |  | 10118443 | [7 empty] | 正常进行 | 0.03 | 303553.29 | 100000 | 100000 | 203553.29 | 4800000 | 4800000 | 1800000 | 1800000 | 17.79% | 1739791 | 1739791 | 1800811 |  |  |  | 1800811 | 0.0374 | 179520 | 179520 | 179520 | 0 |  | 132 | 管庄
2014-05-08 | 项目部表,第115行 | XMF14-14 | 国家体育总局乒乓球馆 | 项目部 | 北京建工集团有限责任公司 | 北京市 | 韩魁 | 北京嘉世弘商贸有限公司 | 韩魁 | 否 |  | 944953.41 |  |  |  | 125391 | 2014-05-14 | 284 |  | 正常进行 | 0.036 | 34018.3228 | 19298.8 | 19298.8 | 14719.5228 | 500000 | 500000 | 500000 | 500000 | 52.91% | 358429.09 | 358429.09 | 404563.09 |  |  |  | 404563.09 | 0.034 | 17000 | 10200 | 10200 | 6800 |  | 4 | 大兴
2014-05-01 | 项目部表,第116行 | XMF14-15 | 双井宿舍楼工程 | 项目部 | 中国国际贸易中心有限公司 | 北京市 | 柯秋惠 | 北京宇光装饰有限公司 | 柯秋惠 | 否 |  | 14986416.53 | [7 empty] | 正常进行 | 0.03 | 449592.4959 |  |  | 449592.4959 |  |  | 0 | 0 | [9 empty] | 0 |  |  | 0 |  | 110 | 三河
2014-05-01 | 项目部表,第117行 | XMF14-16 | 天津武清红星广场示范区 | 项目部 |  | 天津市 | [13 empty] | 正常进行 |  | 0 |  |  | 0 |  |  | 0 | 0 | [9 empty] | 0 |  |  | 0
2014-05-01 | 项目部表,第118行 | XMF14-17 | 大兴旧宫中学改扩建项目 | 项目部 |  | 北京市 | 孙磊 | 北京红星日晟门窗厂 |  |  |  | 769500 |  |  |  | 0446168 | 2014-06-06 | 231 |  | 正常进行 | 0.046 | 35397 | 35397 | 35397 | 0 |  |  | 0 | 0 | [9 empty] | 0 |  |  | 0 |  | 6 | 亦庄
2014-05-20 | 项目部表,第119行 | XMF14-18 | M5样板间外立面幕墙 | 项目部 | 北京五居投资有限公司 | 北京市 | 许谊 | 北京闵铝鑫门窗有限公司 | 许谊 | 否 |  | 520000 |  |  |  | 0446165 | 2014-06-03 | 156 |  | 正常进行 | 0.036 | 18720 | 18720 | 18720 | 0 | 156000 | 156000 | 156000 | 156000 | 30% | 140000 | 140000 | 145304 |  |  |  | 145304 | 0.034 | 5304 | 5304 | 5304 | 0
2014-06-01 | 项目部表,第120行 | XMF14-19 | 东北旺农场科研楼一号楼 | 项目部 | 北京城建道桥建设集团有限公司 | 北京市 | 李金光 | 北京丰益宏业装饰有限公司 | 李金光 | 否 |  | 14800000 | [7 empty] | 正常进行 |  | 0 |  |  | 0 |  |  | 3300000 | 3300000 | 22.3% | 1261050 | 1261050 | 1261050 |  |  |  | 1261050 | 0.034 | 0 |  |  | 0 |  | 44 | 昌平
2014-06-01 | 项目部表,第121行 | XMF14-20 | 61785部队二期经济适用房 | 项目部 |  | 北京市 | 霍林宝 | 中国人民解放军61159部队后勤部 | 霍林宝 | 否 |  | 3326070 | [7 empty] | 正常进行 | 0.036 | 119738.52 |  |  | 119738.52 | 300000 | 300000 | 0 | 0 | [8 empty] | 0.034 | 10200 |  |  | 10200 |  | 35 | 亦庄
2014-06-30 | 项目部表,第122行 | XMF14-21 | 北京中医药大学良乡校区东院 | 项目部 |  | 北京市 | 倪勇 | 上海昂亚装饰有限公司 | 倪勇 | 否 |  | 5305357.6 | [7 empty] | 正常进行 | 0.03 | 159160.728 | 100000 | 100000 | 59160.728 | 1060000 | 1060000 | 1060000 | 1060000 | 19.98% | 356366.43 | 356366.43 | 428446.43 |  |  |  | 428446.43 | 0.034 | 36040 | 36040 | 36040 | 0 |  | 72 | 三河
2014-07-01 | 项目部表,第123行 | XMF14-22 | 天津武清原乡郡项目示范区 | 项目部 |  | 天津市 | 冯国亮 | 三河市益吉装饰工程有限公司 | 冯国亮 |  |  | 743283 | [7 empty] | 正常进行 | 0.036 | 26758.188 |  |  | 26758.188 | 631790.55 | 631790.55 | 0 | 0 | [9 empty] | 0 |  |  | 0 |  | 10 | 三河
2014-07-17 | 项目部表,第124行 | XMF14-23 | 万兴综合楼工程 | 项目部 |  |  | 罗刚 | 北京世纪锦湖装饰工程有限公司 | 罗刚 | [10 empty] | 正常进行 |  | 0 |  |  | 0 |  |  | 0 | 0 | [9 empty] | 0 |  |  | 0
2014-07-17 | 项目部表,第125行 | XMF14-24 | 靓景明居四期 | 项目部 |  | 北京市 | 徐建军 | 高碑店市嘉鑫靓景窗业有限公司 | 李成军 | 否 |  | 5519500 | [7 empty] | 正常进行 | 0.03 | 165585 | 50000 | 50000 | 115585 | 1000000 | 1000000 | 1000000 | 1000000 | 18.12% | 701510.92 | 701510.92 | 735510.92 |  |  |  | 735510.92 | 0.034 | 34000 | 34000 | 34000 | 0 |  | 77 | 管庄
2014-07-17 | 项目部表,第126行 | XMF14-25 | 海淀清河二期B4区 | 项目部 |  | 北京市 | 余斌 | 博洋恒润（北京）幕墙装饰工程有限公司 | 余斌 | 否 |  | 14892896.99 | [7 empty] | 正常进行 |  | 0 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0
2014-07-01 | 项目部表,第127行 | XMF14-26 | 6201工程 | 项目部 | 中国人民解放军战略规划综合局 | 北京市 | 霍林宝 | 中国人民解放军61159部队后勤部 | 霍林宝 | 否 |  | 1885067.2 | [7 empty] | 正常进行 | 0.036 | 67862.4192 |  |  | 67862.4192 | 565520 | 565520 | 0 | 0 | [8 empty] | 0.034 | 19227.68 |  |  | 19227.68 |  | 21 | 亦庄
2014-07-01 | 项目部表,第128行 | XMF14-27 | 21#住宅楼等18项 | 项目部 |  | 北京市 | 李春光 | 北京邦士富生物科技有限公司 | 李玉斌 | 否 |  | 1679000 | [7 empty] | 正常进行 | 0.036 | 60444 |  |  | 60444 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0 |  | 19 | 亦庄
2014-07-01 | 项目部表,第129行 | XMF14-28 | 北京市十一学校改造工程 | 项目部 |  | 北京市 | 王军 | 北京军建凯达幕墙装饰有限公司 | 秦存国 | 否 |  | 1758061 | [7 empty] | 正常进行 | 0.036 | 63290.196 |  |  | 63290.196 | 527418.3 | 527418.3 | 0 | 0 | [8 empty] | 0.034 | 17932.2222 |  |  | 17932.2222
2014-08-04 | 项目部表,第130行 | XMF14-29 | 总政机关东区34号楼断桥铝合金 | 项目部 | 总政机关营建办公室 | 北京市 | 李玉朝 | 北京若愚装饰有限公司 | 杨书芳 | 否 |  | 100000 | [7 empty] | 正常进行 | 0.036 | 3600 |  |  | 3600 |  |  | 0 | 0 | [8 empty] | 0.034 | 0 |  |  | 0